## Sprint 1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
User Story #1 - Customer Registration (8 SP) | 8 |  | 6.5 | 2 | 2 | 1.5 | 0 | 1 | 0 | To Do
Create Customer model/schema | 2 | Akhi | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Done | 2
Create POST /customers endpoint | 3 | Akhi | 2 | 0 | 1 | 0 | 0 | 1 | 0 | Done | 3
Add customer router, load_routes() | 2 | Akhi | 1.5 | 0 | 1 | 0.5 | 0 | 0 | 0 | Doing | 2
Unit test for customer creation | 1 | Akhi | 1 | 0 | 0 | 1 | 0 | 0 | 0 | To Do | 1
User Story #2 - Menu Item Management (13 SP) | 13 |  | 9.5 | 2 | 2 | 2 | 2 | 0 | 0 | To Do
Create MenuItem model/schema | 3 | Akhi | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Done | 3
Create POST /menu_items endpoint | 3 | Akhi | 2 | 0 | 2 | 0 | 0 | 0 | 0 | Done | 3
Create GET /menu_items endpoint | 3 | Akhi | 1.5 | 0 | 0 | 1 | 1 | 0 | 0 | Done | 3
Create router, load_routes() | 2 | Akhi | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Done | 2
Unit tests for menu items | 2 | Akhi | 2 | 0 | 0 | 1 | 1 | 0 | 0 | Done | 2
User Story #3 - Leave a Review (6 SP) | 6 |  | 5.5 | 1 | 2 | 2 | 0.5 | 0 | 0 | To Do
Create Review model/schema | 2 | Tyler | 2 | 1 | 1 | 0 | 0 | 0 | 0 | To Do | 2
Create POST /reviews endpoint | 2 | Tyler | 2 | 0 | 1 | 1 | 0 | 0 | 0 | To Do | 2
Router setup + load_routes() | 1 | Tyler | 1 | 0 | 0 | 1 | 0 | 0 | 0 | To Do | 1
Unit tests for menu reviews | 1 | Tyler | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | To Do | 1
User Story #4 - Ingredient Management (8 SP) | 8 |  | 7 | 1 | 2 | 3 | 1 | 0 | 0 | To Do
Create Ingredient model/schema | 2 | Tithi | 2 | 1 | 1 | 0 | 0 | 0 | 0 | To Do | 2
Create POST /ingredients endpoint | 2 | Tithi | 2 | 0 | 1 | 1 | 0 | 0 | 0 | To Do | 2
Create GET /ingredients endpoint | 2 | Tithi | 1.5 | 0 | 0 | 1 | 0.5 | 0 | 0 | To Do | 2
Add router + unit tests | 2 | Tithi | 1.5 | 0 | 0 | 1 | 0.5 | 0 | 0 | To Do | 2
User Story #5 - View Sandwich Details (6 SP) | 6 |  | 5.5 | 1 | 2.5 | 1 | 1 | 0 | 0 | To Do
Create sandwich router GET /sandwiches | 2 | Dave | 2 | 1 | 1 | 0 | 0 | 0 | 0 | To Do | 2
Update schema for nested ingredient view | 1 | Dave | 1 | 0 | 1 | 0 | 0 | 0 | 0 | To Do | 1
Unit test: view sandwich + ingredients | 2 | Dave | 2 | 0 | 0 | 1 | 1 | 0 | 0 | To Do | 2
Add router + unit tests | 1 | Dave | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | To Do | 1
TOTAL |  |  | 34 | 7 | 10.5 | 9.5 | 4.5 | 1 | 0 |  | 14

## Sprint 2
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
User Story #6 -Order Management (13 SP) | 13 |  | 9 | 2 | 2 | 2 | 1.5 | 1 | 0.5 | To Do
Create Order model/schema | 3 | Akhi | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 3
Implement POST /orders endpoint | 3 | Akhi | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 3
Implement GET /orders endpoint | 2 | Akhi | 1.5 | 0 | 0 | 1 | 0.5 | 0 | 0 | Doing | 2
Implement GET /orders/{id} | 2 | Akhi | 1.5 | 0 | 0 | 1 | 0.5 | 0 | 0 | Done | 2
Wire up order router + load_routes() | 1 | Akhi | 0.5 | 0 | 0 |  | 0.5 | 0 | 0 | Done | 1
Unit test for orders (test_orders) | 2 | Akhi | 1.5 | 0 | 0 | 0 | 0 | 1 | 0.5 | Done | 2
User Story #7 - Update Customer Information (5 SP) | 5 |  | 3 | 2 | 1 | 0 | 0 | 0 | 0 | To Do
Implement PUT /customers/{id} | 3 | Akhi | 1.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | Done | 3
Add schema for customer update | 1 | Akhi | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | Done | 1
Unit test for customer update | 1 | Akhi | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | Done | 1
User Story #8 - Delete Review (3 SP) | 3 |  | 1.5 | 0.75 | 0.75 | 1 | 0 | 0 | 0 | To Do
Implement DELETE /reviews/{id} | 2 | Tyler | 1 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | To Do | 2
Unit test for deleting review | 1 | Tyler | 0.5 | 0.25 | 0.25 | 1 | 0 | 0 | 0 | To Do | 1
User Story #9 - Update Ingredient (5 SP) | 5 |  | 3 | 1 | 2 | 0 | 0 | 0 | 0 | To Do
Implement PUT /ingredients/{id} | 3 | Tithi | 2 | 1 | 1 | 0 | 0 | 0 | 0 | To Do | 3
Unit test for updating ingredient | 2 | Tithi | 1 | 0 | 1 | 0 | 0 | 0 | 0 | To Do | 2
User Story #10 - Search Sandwich by ID (4 SP) | 4 |  | 2.5 | 1 | 1 | 0.5 | 0 | 0 | 0 | To Do
Implement GET /sandwiches/{id} | 3 | Dave | 1.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | To Do | 3
Unit test for sandwich retrieval by ID | 1 | Dave | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | To Do | 1
User Story #11 - Search Sandwich by ID (4 SP) | 4 |  | 2.5 | 1 | 1 | 0.5 | 0 | 0 | 0 | To Do
Implement GET /sandwiches/{id} | 3 | Dave | 1.5 | 1 | 0.5 | 0 | 0 | 0 | 0 | To Do | 3
Unit test for sandwich retrieval by ID | 1 | Dave | 1 | 0 | 0.5 | 0.5 | 0 | 0 | 0 | To Do | 1
TOTAL |  |  | 19 | 6.75 | 6.75 | 3.5 | 1.5 | 1 | 0.5 |  | 14